## Sheet1
Project Name: | Full Metal Library
Stakeholders: | Users, Product Owner, Scrum Master, Scrum Team
Created by: | Solid State Development
Product Owner: | Richa Panjabi
Scrum Master: | Dave Sushames
Epic | User Story ID | Feature/Title | User Story | Story Points | Sprint | Member
Users should be able to log into the site. | US001 | New Admin able to register an account | As a new administrator, I want to register to the application, so that I can use it. | 3 | 2 | Shontelle
| US002 | Registered Admin can login | As an admin, I want to login the website, so that I can use the full functionality of the application. | 2 | 2 | Shontelle
| US003 | Registered Admin can logout | As an Admin I want to log out of the FML webpage when I'm done using it, so that other users can log in. | 1 | 2 | Shontelle
Users should be able to manage Books. | US004 | Registered Admin can Create new Books. | As an admin, I want to add new books to the library catalogue, so that people can check them out. | 1 | 1 | Dave
| US005 | Registered Admin can Edit book information. | As an admin, I want to edit book information, so that I can fix any errors. | 1 | 1 | Dave
| US006 | Registered Admin can Delete books. | As an admin, I want to delete books including their details, so that I can remove missing/damaged books from the catalogue. | 1 | 1 | Dave
| US007 | Registered Admin can Search the books. | As a user, I want to search for books by keyword, so that I can search catalogue. | 2 | 2 | Dave
| US008 | Registered Admin can Sort the book catalogue. | As an Admin, I want to sort the books in the catalogue according to Title and Author. | 1 | 2 | Dave
Users should be able to manage Authors | US009 | Registered Admin can Create new Authors. | As an admin, I want to add new authors to the library catalogue, so that people can see who wrote a book. | 1 | 1 | Sachith
| US010 | Registered Admin can Edit author information. | As an admin, I want to edit authors information, so that I can fix any errors. | 1 | 1 | Sachith
| US011 | Registered Admin can Delete authors. | As an admin, I want to delete books including their details, so that I can remove incorrect authors from the system. | 1 | 1 | Sachith
| US012 | Registered Admin can Search the authors. | As a user, I want to search for authors by keyword, so that I can search for a specific author easier. | 2 | 2 | Sachith
| US013 | Registered Admin can Sort the author catalogue. | As an Admin, I want to sort the authors in the catalogue according to First and Last name. | 1 | 2 | Sachith
Users should be able to manage accounts to sign in with | US014 | Registered Admin can Create new Admins. | As an admin, I want to add new admins to the list, so that I can sign in with different accounts. | 1 | 1 | Shontelle
| US015 | Registered Admin can Edit Admin information. | As an admin, I want to edit admin information, so that I can change my username/password | 1 | 1 | Shontelle
| US016 | Registered Admin can Delete admins. | As an admin, I want to delete admins including their details, so that users can't sign in with the account any more | 1 | 1 | Shontelle
| US017 | Registered Admin can Disable the admins. | As an admin, I want to disable admin accounts, to prevent people signing in with them, while not fully deleting the account | 1 | 2 | Shontelle
| US018 | Registered Admin can Search the admins. | As a user, I want to search for admins by keyword, so that I can search for a specific account easier. | 2 | 2 | Shontelle
| US019 | Registered Admin can Sort the admin catalogue. | As an Admin, I want to sort the admins in the catalogue according to Username | 1 | 2 | Shontelle
Reasoning behind priority setting method: The CRUD implementation for the Book, Author, and Admin classes would be easy to implement, so we decided to put them in the first sprint. The Search/Sort functionality would be a little harder, and also requires the pages to be set up first, so that went in sprint 2.