## Week#1
Question | Person | Week 1 : 8/9/25 ~ 12/9/25
|  | Mon | Tue | Wed | Thur | Fri
What have you done? | Dave | - | Made user stories | Create Books Class |  | Implement SCUD for Class
| Sachith | - | Made user stories | Create Authors Class |  | Implement SCUD for Class
| Shontelle | - | Made user stories | Create Admins Class |  | Implement SCUD for Class
What will you do next? | Dave | - | Create Books Class | Implement SCUD for Class |  | Input Validation
| Sachith | - | Create Authors Class | Implement SCUD for Class |  | Add Search/Sort method
| Shontelle | - | Create Admins Class | Implement SCUD for Class |  | Sort Controllers/Views
Do you have any obstacles? | Dave | - | - |  |  | Issues with it trying to use someone else's filepath
| Sachith | - | - | Issues with database
| Shontelle | - | - | Figuring out GitHub
Sprint Review
First week, getting a Solution file made. Implemented SCUD.
Sprint Retrospective
Team figuring out how to work together, learning each other's specialities

## Week#2
Question | Person | Week 2 : 15/9/25 ~ 19/9/25
|  | Mon | Tue | Wed | Thur | Fri
What have you done? | Dave | - | Input Validation |  |  | Beautified homepage
| Sachith |  | Add Search/Sort method |  |  | Added login/register page
| Shontelle |  | Sort Controllers/Views |  |  | Made Test plan
What will you do next? | Dave | - | Beautify homepage |  |  | Started on tests
| Sachith | - | Add login/register page |  |  | Started on tests
| Shontelle | - | Make Test plan |  |  | Started on tests
Do you have any obstacles? | Dave | - | Same issue with foreign filepaths
| Sachith | - | -
| Shontelle | - | -
Sprint Summary
Second week, finished the app. It works now. Mostly
Sprint Retrospective
Team locked in and completed their respective pages ahead of time, time for testing! :3

## Week#3
Question | Person | Week 3 : 22/9/25 ~ 26/9/25
|  | Mon | Tue | Wed | Thur | Fri
What have you done? | Dave | Started on tests |  | Work on tests |  | Finished Blackbox Tests
| Sachith |  |  | Sorted inconsistencies with Login/Registration messages |  | Finished Blackbox Tests
| Shontelle | Started on tests |  | Work on tests |  | Finished Blackbox Tests
What will you do next? | Dave | Work on tests |  | Finish blackbox tests
| Sachith | Sort inconsistencies with Login/Registration messages | - | Finish blackbox tests
| Shontelle | Work on tests | - | Finish blackbox tests
Do you have any obstacles? | Dave |  |  | Finally sorted out the foreign filepath issue
| Sachith | - | -
| Shontelle | - | -
Sprint Summary
Third week, bugfixing and starting on tests.
Sprint Retrospective
Team noticed a few bugs with the login/registration, had to fix mid blackbox tests.

## Week#4
Question | Person | Week 4 : 29/9/25 ~ 3/10/25
|  | Mon | Tue | Wed | Thur | Fri
What have you done? | Dave | Finished Whitebox tests | Some documentation |  |  | Finished Unit tests
| Sachith | Finished Whitebox tests |  |  |  | Finished Unit tests
| Shontelle | Finished Whitebox tests |  |  |  | Finished Unit tests
What will you do next? | Dave | Documentation | Unit testing |  |  | Static code analysis
| Sachith |  | Unit testing |  |  | Auto tests
| Shontelle |  | Unit testing |  |  | Auto tests
Do you have any obstacles? | Dave
| Sachith | Couldn't access moodle for some reason | -
| Shontelle | - | -
Sprint Summary
Getting stuck into the testing
Sprint Retrospective
Team disheartened to learn that Whitebox wasn't required, after spending so much effort on them. Re-learning how Unit tests work.

## Week#5
Question | Person | Week 4 : 6/10/25 ~ 12/10/25
|  | Mon | Tue | Wed | Thur | Fri | Sat | Sun
What have you done? | Dave |  | Finished Static Code Analysis | Auto tests | Finished Auto tests |  | Documentation done | Finished Presentation
| Sachith |  | Auto tests | Auto tests | Finished Auto tests |  | Documentation done | Finished Presentation
| Shontelle |  | Auto tests | Auto tests | Finished Auto tests |  | Finished test report | Finished Presentation
What will you do next? | Dave |  | More auto tests | More auto tests | Last minute documentation |  | Presentation
| Sachith |  | More auto tests | More auto tests | Last minute documentation |  | Presentation
| Shontelle |  | More auto tests | More auto tests | Finishing off Test Report Conclusion |  | Presentation
Do you have any obstacles? | Dave | Auto tests weren't running properly |  | Auto tests weren't running properly
| Sachith |  | - | Auto tests weren't running properly | Had some issues with github
| Shontelle | - | -
Sprint Summary
Finishing off testing and getting onto documentation
Sprint Retrospective
Last minute frenzy to get the assignment done on time.