## Sheet1
Project Name: | A+ Money Management App
Stakeholders: | Users, Product Owner, Scrum Master, Scrum Team
Created by: | A+ Team
Product Owner: | Christine Villarosa
Scrum Master: | Will Wang
Epic | User Story ID | Feature/Title | User Story | Story Points | Sprint
The A+ Money website will be when a new user is able to set the goal and save the statement, control the details | US001 | First time visitor as a guest user without having to register | As a First-time guest, I want to browse the website without registering. So that I can decide if I want to register to use the website. | 2 | 1
| US002 | New user can register to use the application | As a user, I want to register to the application, so that I can use the application. | 1 | 1
| US003 | Registered User can login | As a user, I want to login the website, so that I can use the full functionality of the application. | 2 | 1
| US004 | Registered User can Create goals. | As a user, I want to input my goal, budget, and time constraints of my goal, so that I can set up my goals. | 2 | 2
| US005 | Registered User can set up the statement. | As a user, I want to input my saving and spending, so that I can set up my statement. | 2 | 2
| US006 | Registered User can set up the details of goals. | As a user, I want to check my goal names, budget, savings, spending, and the time constraints of my goal, so that I can check the details of goals | 3 | 2
| US007 | Registered User can edit the goals. | As a user, I want to edit my goal names, budget, savings, spending, and the time constraints of my goal, so that I can edit my goals. | 3 | 3
| US008 | Registered User can delete the goals. | As a user, I want to delete my goal including its details, so that I can delete my goals. | 3 | 3
| US009 | Registered User can Search the goals. | As a user, I want to search for my goals when I created goals, so that I can search the goals. | 3 | 3
| US010 | Registered User can Sort the goals. | As a user, I want to sort my goals according to the goal date and budget, so that I can sort the goals. | 3 | 3
| US011 | Registered User can logout | As a user, I want to logout the website when I don't want to use the website so that I can use logout. | 3 | 3
| US012 | User can input their data in a securely (encryption and decryption). | As a user, I want to be able to share my information into the website securely so that I can input my information. | 4 | 4